## WBS
Level | WBS Code | Task | Best Case Estimate a | Most Likely Estimate m | Worst Case Estimate b | E Value | SD Value | Task Estimate 95% Confidence
1 | 1 | Design
2 | 1.1 | Design classes | 1 | 2 | 3 | 4 | 0.33333
2 | 1.2 | Design database | 1.5 | 2 | 3.5 | 4.3333 | 0.33333
2 | 1.3 | Design flow activity
3 | 1.3.1 | Login | 0.5 | 1 | 1.5 | 2 | 0.16667
3 | 1.3.2 | Signout | 0.05 | 0.1 | 0.2 | 0.21667 | 0.025
3 | 1.3.3 | Signup | 1 | 1.5 | 2 | 3 | 0.16667
3 | 1.3.4 | Search
3 | 1.3.5 | Book a ticket
3 | 1.3.6 | Cancel a reservation
3 | 1.3.7 | Modify a reservation
3 | 1.3.8 | List of the reservation (Admin/ Client)
3 | 1.3.9 | Contact
3 | 1.3.10 | Create a ticket
3 | 1.3.11 | Modify a ticket
3 | 1.3.12 | Deactivation a ticket
3 | 1.3.13 | Modify profile
2 | 1.4 | Design interface
3 | 1.4.1 | Home
3 | 1.4.2 | Login
3 | 1.4.3 | Signup
3 | 1.4.4 | Reservation
3 | 1.4.5 | Search
3 | 1.4.6 | Result of search
3 | 1.4.7 | Manager reservation (Admin/ Client)
3 | 1.4.8 | Manager account
3 | 1.4.9 | Create/ Update a ticket
3 | 1.4.10 | Contact
1 | 2 | Implemention
2 | 2.1 | Create database
2 | 2.2 | Code fonctions
3 | 2.2.1 | Login
4 | 2.2.1.1 | Interface
4 | 2.2.1.2 | Code business
4 | 2.2.1.3 | Test unit
3 | 2.2.2 | Signup
4 | 2.2.2.1 | Interface
4 | 2.2.2.2 | Code business
4 | 2.2.2.3 | Test unit
3 | 2.2.3 | Search
4 | 2.2.3.1 | Interface
4 | 2.2.3.2 | Code business
4 | 2.2.3.3 | Test unit |  |  |  | Create a ticket
3 | 2.2.4 | Book a ticket |  |  |  | Modify a ticket
4 | 2.2.4.1 | Interface |  |  |  | Deactivation a ticket
4 | 2.2.4.2 | Code business |  |  |  | Modify profile
4 | 2.2.4.3 | Test unit
3 | 2.2.5 | Modify a reservation
4 | 2.2.5.1 | Code business
4 | 2.2.5.2 | Test unit
3 | 2.2.6 | Cancel a reservation
4 | 2.2.6.1 | Code business
4 | 2.2..6.2 | Test unit
3 | 2.2.7 | List of the reservation Client
4 | 2.2.7.1 | Interface
4 | 2.2.7.2 | Code business
4 | 2.2.7.3 | Test unit
3 | 2.2.8 | List of the reservation Admin
4 | 2.2.8.1 | Code business
4 | 2.2.8.2 | Test unit
3 | 2.2.9 | Contact
4 | 2.2.9.1 | Interface
4 | 2.2.9.2 | Code business
4 | 2.2.9.3 | Test unit
3 | 2.2.10